{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["نسخه اول"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"نسخه اول","index":0,"n_rows":10,"n_cols":7,"rows_kept":10,"cut":false,"hidden":false,"merged":[]}
["مراحل","هفته",null,"شروع",null,"پايان","نمودار تعداد روزهاي هر مرحله"]
["مرحله اول: انتخاب كليدواژه‌ها و جستجو در منابع",2,"2018-06-25",{"$f":"ToShamsi(C2)","v":"4 تير 1397"},{"$f":"C2+(B2*7)","v":"2018-07-09"},{"$f":"ToShamsi(E2)","v":"18 تير 1397"},{"$f":"B2*7","v":14}]
["مرحله دوم: جمع‌آوري فيش‌ها و آماده‌سازي اوليه به صورت تايپي",1,{"$f":"E2+1","v":"2018-07-10"},{"$f":"ToShamsi(C3)","v":"19 تير 1397"},{"$f":"C3+(B3*7)","v":"2018-07-17"},{"$f":"ToShamsi(E3)","v":"26 تير 1397"},{"$f":"B3*7","v":7}]
["مرحله سوّم: عنوان‌گذاري فيش‌ها، جهت تسهيل در درك مطلب",1,{"$f":"E3+1","v":"2018-07-18"},{"$f":"ToShamsi(C4)","v":"27 تير 1397"},{"$f":"C4+(B4*7)","v":"2018-07-25"},{"$f":"ToShamsi(E4)","v":"3 مرداد 1397"},7]
["مرحله چهارم: دسته‌بندي عناوين، جهت تسهيل در مباحثه",1,"2018-07-26","4 مرداد 1397","2018-08-02","11 مرداد 1397",7]
["مرحله پنجم: مباحثه هفتگي بر روي عناوين فيش‌ها",10,"2018-08-03","12 مرداد 1397","2018-10-12","20 مهر 1397",70]
["مرحله ششم: جمع‌بندي نتايج مباحثات و مرور نهايي در جلسه مشترك",2,"2018-10-13","21 مهر 1397","2018-10-27","5 آبان 1397",14]
["مرحله هفتم: نگارش متن جمع‌بندي شده از مباحثات و تدوين محصول نهايي",2,"2018-10-28","6 آبان 1397","2018-11-11","20 آبان 1397",14]
["مرحله هشتم: بررسي متن توسط كارفرما و ويرايش و اصلاح آن",10,"2018-11-12","21 آبان 1397","2019-01-21","1 بهمن 1397",70]
["مرحله نهم: صفحه‌بندي و تنظيمات ظاهري متن",1,"2019-01-22","2 بهمن 1397","2019-01-29","9 بهمن 1397",7]