{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":17,"n_cols":6,"rows_kept":17,"cut":false,"hidden":false,"merged":[]}
["عنوان فعاليت","مدّت","start","آغاز","end","پايان"]
["1. توليد سند چشم‌انداز",2,"2022-02-09",{"$f":"toshamsi(C2)","v":"20 بهمن 1400"},{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-02-11"},{"$f":"toshamsi(E2)","v":"22 بهمن 1400"}]
["2. تصويب سند چشم‌انداز",6,{"$f":"E2+1","v":"2022-02-12"},{"$f":"toshamsi(C3)","v":"23 بهمن 1400"},{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-02-18"},"29 بهمن 1400"]
["3. توليد سند راهبردي",3,{"$f":"E3+1","v":"2022-02-19"},"30 بهمن 1400",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-02-22"},"3 اسفند 1400"]
["4. تصويب سند راهبردي",7,"2022-02-23","4 اسفند 1400",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-03-02"},"11 اسفند 1400"]
["5. توليد برنامه پژوهشي",5,"2022-03-03","12 اسفند 1400",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-03-08"},"17 اسفند 1400"]
["6. توليد برنامه آموزشي",15,"2022-03-09","18 اسفند 1400",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-03-24"},"4 فروردين 1401"]
["7. توليد برنامه رسانه‌اي",5,"2022-03-25","5 فروردين 1401",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-03-30"},"10 فروردين 1401"]
["8. توليد برنامه اداري",3,"2022-03-31","11 فروردين 1401",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-04-03"},"14 فروردين 1401"]
["9. توليد سند نهايي برنامه",2,"2022-04-04","15 فروردين 1401",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-04-06"},"17 فروردين 1401"]
["10. تصويب سند برنامه‌ها",30,"2022-04-07","18 فروردين 1401",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-05-07"},"17 ارديبهشت 1401"]
["11. توليد چارت سازماني",5,"2022-05-08","18 ارديبهشت 1401",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-05-13"},"23 ارديبهشت 1401"]
["12. تصويب چارت سازماني",7,"2022-05-14","24 ارديبهشت 1401",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-05-21"},"31 ارديبهشت 1401"]
["13. توليد شرح وظايف",10,"2022-05-22","1 خرداد 1401",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-06-01"},"11 خرداد 1401"]
["14. تصويب شرح وظايف",15,"2022-06-02","12 خرداد 1401",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-06-17"},"27 خرداد 1401"]
["15. توليد سند نهايي مؤسسه",7,"2022-06-18","28 خرداد 1401",{"$f":"Table1[[#This Row],[start]]+Table1[[#This Row],[مدّت]]","v":"2022-06-25"},"4 تير 1401"]
["كل مدّت پروژه",{"$f":"SUBTOTAL(109,B2:B16)","v":122},{"$f":"C2","v":"2022-02-09"},{"$f":"toshamsi(C17)","v":"20 بهمن 1400"},{"$f":"E16","v":"2022-06-25"},"4 تير 1401"]